## Pre-Load Tasks
Sl# | Area | Supplier | Owner | Task Name | Status | Date | Comments
Pre Load Activities
1 | Fusion | Version1 | Kiran Jagadeesan | Enable DM user accounts | Completed | 2019-04-29 | From Steve Cornish
2 | Fusion | Version1 | Kiran Jagadeesan | Enable HCM_IMPL5 account for Dawn with Security Console | Completed | 2019-05-06
3 | Fusion | Version1 | Duncan Davies | Obtain email confirmation from Symatrix on HCM configuration status | Completed | 2019-05-06 | Moved to EOD 8th May as per Duncan's email
4 | Fusion | Version1 | Kiran Jagadeesan | Verify the lookup code DATA_MIGRATION is added to the lookup type HRC_SOURCE_SYSTEM_OWNER | Completed | 2019-05-06
5 | Fusion | Version1 | Kiran Jagadeesan | Verify the positions EFF is deployed | Completed | 2019-05-06
6 | Fusion | Version1 | Kiran Jagadeesan | Verify the Worker auto numbering is disabled | Completed | 2019-05-06
7 | Fusion | Version1 | Kiran Jagadeesan | Verify the bank account encryption is disabled | Completed | 2019-05-06
8 | Fusion | Version1 | Kiran Jagadeesan | Verify the Lloyds bank number is corrected as per the RFC | Completed | 2019-05-06
9 | Fusion | Version1 | Kiran Jagadeesan | Check that Position Costing DFF is deployed correctly | Completed | 2019-05-06
10 | Share Point | UoB | Ana/Sophia | Loading of Work Schedules master data | Completed | 2019-05-08
11 | Share Point | UoB | Ana/Sophia | Loading/Updating of all departments (start date as 01-Jan-1951) | Completed | 2019-05-08
12 | Share Point | UoB | Andy Ludlow | Obtain the latest Job, Department (including the default expense accounts) & Element costing files | Completed | 2019-05-08
13 | Fusion | UoB | Andy Ludlow | Load/Update employee default expense account master data (segment values) | Completed | 2019-05-08
14 | Share Point | UoB | Andy Ludlow | Obtain the latest Position and Assignment Costing Overrides (to be shared with Gary Murphy) | Completed | 2019-05-08
15 | Share Point | UoB | Mike Dean | Obtain the latest Bank data file | Completed | 2019-05-08
16 | Share Point | Version1 | Trevor Watson | Obtain the up-to date Location data file | Completed | 2019-05-08
17 | Fusion | UoB | Andy Ludlow | Load of cost centre DFF’s | Completed | 2019-05-08
18 | AlataHRN | UoB | Gary Murphy | Leavers process execution (if needed) | Completed | 2019-05-12
19 | Share Point | UoB | Lesley Driscoll | Obtain the latest Assignment Schedules/Accrual Plan/Assignment Category data file | Completed | 2019-05-13
20 | Share Point | UoB | Gary Murphy | Obtain the latest Timecard data for cacuals | Completed | 2019-05-13
21 | Share Point | UoB | Gemma Harrison | Obtain the upto date benefits spreadsheet for Court Orders | Completed | 2019-05-13
22 | AlataHRN | UoB | Gary Murphy | Disable AltaHRN nightly refresh process | Completed | 2019-05-13
23 | AlataHRN | UoB | Gary Murphy | Refresh mapping tables (All, including balances made up-to date) | Completed | 2019-05-13
24 | AlataHRN | UoB | Gary Murphy | UoB to perform sanity check on the mapping tables | Completed | 2019-05-13
25 | AlataHRN | UoB | Tim Hall/UoB | Take the snapshot of the current stage and baseline for the DM activity (DM_BASELINE_11 & 12) | Completed | 2019-05-13
26 | AlataHRN | Version1 | Kiran Jagadeesan | V1 to perform sanity check on the mapping tables | Completed | 2019-05-14
27 | AlataHRN | UoB | Dawn Hopkins | Final go ahead from UoB | Completed | 2019-05-14

## HCM Load
Status
Sl# | Area | Supplier | Owner | Task Name | Load | Recon | Date | Time (IST) | Duration | Comments | Records | Loaded | Failed | Load % | MTM Defects
Data Load - Day 1
1 | Fusion | Version1 | Siva | Location | Completed | Completed | 2019-05-14 | 08:30 - 11:00 | 120 | Revised data received from finance team | 397 | 397 | 0 | 100
2 | Fusion | Version1 | Madhu | GB Banks | Completed | Completed | 2019-05-14 | 11:00 - 12:00 | 60 | Only GB Banks | 382 | 382 | 0 | 100
3 | Fusion | Version1 | Madhu | GB Bank Branches | Completed | Completed | 2019-05-14 | 13:30 - 14:00 | 60 | Only GB branches | 17554 | 17554 | 0 | 100
4 | Fusion | Version1 | Subba | Foreign Banks | Completed | Completed | 2019-05-14 | 14:30 - 15:30 | 60 | Non GB Banks | 87 | 87 | 0 | 100
5 | Fusion | Version1 | Subba | Foreign Bank Branches | Completed | Completed | 2019-05-14 | 15:30 - 16:30 | 60 | Non GB Bank Branches | 89 | 89 | 0 | 100
6 | Fusion | Version1 | Madhu | Department Costing | Completed | Completed | 2019-05-14 | 09:00 - 10:00 | 60 |  | 371 | 371 | 0 | 100
7 | Fusion | Version1 | Madhu | Job Costing | Completed | Completed | 2019-05-14 | 10:00 - 11:00 | 60 |  | 437 | 437 | 0 | 100
8 | Fusion | Version1 | Subba | Element Costing | Completed | Completed | 2019-05-14 | 11:00 - 12:00 | 60 |  | 1912 | 1912 | 0 | 100
9 | Fusion | Version1 | Natarajan | 3rd Party Organisations | Completed | Completed | 2019-05-14 | 9:00 - 10:00 | 60 |  | 18 | 18 | 0 | 100
10 | Fusion | Version1 | Natarajan | 3rd Party Organisation Address | Completed | Completed | 2019-05-14 | 11:00 - 12:00 | 60 |  | 18 | 18 | 0 | 100
11 | Fusion | Version1 | Natarajan | 3rd Party Payment Methods | Completed | Completed | 2019-05-14 | 13:00 - 14:00 | 60 |  | 18 | 18 | 0 | 100
12 | Fusion | Version1 | Siva | Positions | Completed | Completed | 2019-05-14 | 09:00 - 12:00 | 180 |  | 15479 | 15479 | 0 | 100
13 | Fusion | Version1 | Siva | Position Costing | Completed | Completed | 2019-05-14 | 13:00 - 14:30 | 90 |  | 1851 | 1851 | 0 | 100
14 | Fusion | Version1 | Madhu/Siva | Log & Error Report Extraction/Analysis for the load completed | Completed | Completed | 2019-05-14 | 13:00 - 18:00 | 300
15 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-14 | 09:00 - 18:00 | Full Day
Data Load - Day 2
16 | Fusion | Version1 | Siva | Worker | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  | 26200 | 26123 | 77 | 99.71 | 21004
17 | Fusion | Version1 | Siva | Name | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
18 | Fusion | Version1 | Siva | Legislative Data | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
19 | Fusion | Version1 | Siva | Address | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
20 | Fusion | Version1 | Siva | Email | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
21 | Fusion | Version1 | Siva | Phone | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
22 | Fusion | Version1 | Siva | National Identifier | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
23 | Fusion | Version1 | Siva | Citizenship | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
24 | Fusion | Version1 | Siva | Visa | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
25 | Fusion | Version1 | Siva | Passport | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
26 | Fusion | Version1 | Siva | Ethnicity | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
27 | Fusion | Version1 | Siva | Religion | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
28 | Fusion | Version1 | Siva | Work Relationship | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
29 | Fusion | Version1 | Siva | Assignments | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
30 | Fusion | Version1 | Siva | Worker Extra Information | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day |  |  |  |  | N/A
31 | Fusion | Version1 | Siva | Assignment Work Measure | Completed | Completed | 2019-05-15 | 9:00 - 17:00 | Full Day
32 | Fusion | Version1 | Siva | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-15 | 13:00 - 18:00 | 300
33 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-16 | 09:00 - 18:00 | Full Day | This task may not complete on the same day
Data Load - Day 3
34 | Fusion | Version1 | Madhu | Talent Profile | Completed | Completed | 2019-05-16 | 9:00 - 10:00 | 60 |  | 11722 | 11722 | 0 | 100
35 | Fusion | Version1 | Madhu | External Identifier | Completed | Completed | 2019-05-16 | 10:30 - 11:30 | 60 |  | 21707 | 21707 | 0 | 100
36 | Fusion | Version1 | Madhu | Disability | Completed | Completed | 2019-05-16 | 12:00 - 13:00 | 60 |  | 26243 | 26243 | 0 | 100
37 | Fusion | Version1 | Madhu | Document Preference | Completed | Completed | 2019-05-16 | 14:00 - 15:00 | 60 |  | 71757 | 71757 | 0 | 100
38 | Fusion | Version1 | Madhu | Schedule Assignment | Completed | Completed | 2019-05-16 | 15:30 - 16:30 | 60 |  | 13561 | 13561 | 0 | 100
39 | Fusion | Version1 | Natarajan | Synchronize Person Records | Completed |  | 2019-05-17 | 16:30 - 18:00 | 90 | ESS Job
40 | Fusion | Version1 | Natarajan | Maintain Party and Location Current Record Information | Completed |  | 2019-05-17 | 18:00 - 18:30 | 30 | ESS Job
41 | Fusion | Version1 | Madhu | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-17 | 17:00 - 18:00 | 60
42 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-17 | 12:00 - 18:00 | 240
Data Load - Day 4
43 | Fusion | Version1 | Siva | Payroll | Completed | Completed | 2019-05-17 | 11:00 - 12:00 | 60 |  | 35133 | 35133 | 0 | 100
44 | Fusion | Version1 | Siva | Salary | Completed | Completed | 2019-05-17 | 12:30 - 13:30 | 60 |  | 57393 | 57393 | 0 | 100
45 | Fusion | Version1 | Madhu | External Bank | Completed | Completed | 2019-05-17 | 9:00 - 13:00 | 180 |  | 22197 | 22197 | 0 | 100
46 | Fusion | Version1 | Madhu | Personal Payment Methods | Completed | Completed | 2019-05-17 | 13:30 - 15:00 | 90 |  | 21867 | 21867 | 0 | 100
47 | Fusion | Version1 | Madhu | User | Completed | Completed | 2019-05-17 | 17:00 - 17:30 | 30 |  | 23605 | 23486 | 119 | 99.5 | 119 Future records
48 | Fusion | Version1 | Natarajan | Send Pending LDAP Requests | Completed |  | 2019-05-17 | 18:00 - 03:00 | 540 | ESS Job (long running job, may take up to 9 hours) |  |  | 0 | #DIV/0!
49 | Fusion | Version1 | Madhu/Siva | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-17 | 15:30 - 17:00 | 90
50 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-18 | 14:30 - 18:30 | 240
Data Load - Day 5
51 | Fusion | Version1 | Madhu | SD Calculation Card - Component & Association | Completed | Completed | 2019-05-18 | 9:00 - 11:00 | 120 |  | 41578 | 41578 | 0 | 100
52 | Fusion | Version1 | Madhu | SD Calculation Card - NI Category Update | Completed | Completed | 2019-05-18 | 11:00 - 12:00 | 60 |  | 13739 | 13739 | 0 | 100
53 | Fusion | Version1 | Siva | SD Calculation Card - NI Certificate Update | Completed | Completed | 2019-05-18 | 12:00 - 12:30 | 30 |  | 320 | 320 | 0 | 100
54 | Fusion | Version1 | Siva | Benefits & Pension Calc Card | Completed | Completed | 2019-05-18 | 12:30 - 14:00 | 90 |  | 10806 | 10798 | 8 | 99.93 | 21129
55 | Fusion | Version1 | Madhu | PAE Calculation Card | Completed | Completed | 2019-05-18 | 14:00 - 15:30 | 90 |  | 16699 | 16674 | 25 | 99.85 | 21128
56 | Fusion | Version1 | Siva | CO Calculation card | Completed | Completed | 2019-05-18 | 15:30 - 16:30 | 60 |  | 24 | 16 | 8 | 66.67
57 | Fusion | Version1 | Siva | SL Calculation Card | Completed | Completed | 2019-05-18 | 17:00 - 18:00 | 60 |  | 2149 | 2149 | 0 | 100
58 | Fusion | Version1 | Madhu/Siva | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-18 | 16:00 - 18:00 | 120
59 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-19 | 14:00 - 18:00 | 240
Data Load - Day 6
60 | Fusion | Version1 | Madhu | Accrual Plan Enrolment | Completed | Completed | 2019-05-19 | 09:00 - 10:00 | 60 |  | 7991 | 7960 | 31 | 99.61 | 21131
61 | Fusion | Version1 | Siva | Element Entry | Completed | Completed | 2019-05-19 | 13:00 - 17:00 | 240 |  | 11040 | 10980 | 60 | 99.46 | 21132
62 | Fusion | Version1 | Madhu/Siva | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-19 | 17:30 - 18:30 | 60
63 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-19 | 14:00 - 18:00 | 240 | Task may not finish the same day
Data Load - Day 7
64 | Fusion | Version1 | Siva | Balances | Completed | Completed | 2019-05-20 | 9:00 - 18:00 | Full Day |  | 179974 | 179974 | 0 | 100
65 | Fusion | Version1 | Kiran | Notify HCM functional team to run Benefits Relationship process | Completed |  | 2019-05-18 | 14:00 - 14:30 |  | Email/Phone Communication
66 | Fusion | Symatrix | Chris | Run Benefits Relationship process in HCM | Completed |  | 2019-05-18 | 15:00 - 17:00 | 120 | ESS Job
67 | Fusion | Version1 | Siva | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-20 | 18:30 - 19:30 | 60
68 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-20 | 14:00 - 18:00 | 240
Data Load - Day 8
69 | Fusion | Version1 | Madhu | Benefit - Dental | Completed | Completed | 2019-05-19 | 11:00 - 12:00 | 60 |  | 105 | 98 | 7 | 93.33 | 21133
70 | Fusion | Version1 | Madhu | Benefit - GAYE | Completed | Completed | 2019-05-19 | 12:00 - 13:00 | 60 |  | 79 | 79 | 0 | 100
71 | Fusion | Version1 | Madhu | Benefit - Carpark | Completed | Completed | 2019-05-19 | 13:30 - 14:30 | 60 |  | 1337 | 1335 | 2 | 99.85 | 21133
72 | Fusion | Version1 | Madhu | Benefit - BHSF | Completed | Completed | 2019-05-19 | 15:30 - 16:30 | 60 |  | 373 | 373 | 0 | 100
73 | Fusion | Version1 | Madhu | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-19 | 18:00 - 19:00 | 60
74 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-19 | 14:00 - 18:00 | 240
Data Load - Day 9
75 | Fusion | Version1 | Siva | Assignment Grade Steps | Completed | Completed | 2019-05-20 | 9:00 - 12:00 | 180 |  | 10737 | 10642 | 95 | 99.12 | 21149
76 | Fusion | Version1 | Siva | Assignment Supervisor | Completed | Completed | 2019-05-21 | 12:30 - 15:30 | 180 |  | 6705 | 6687 | 18 | 99.73 | 21152
77 | Fusion | Version1 | Natarajan | Autoprovision Roles for All Users | Completed |  | 2019-05-21 | 16:00 - 16:30 | 240 | ESS Job
78 | Fusion | Version1 |  | Send Personal Data for Multiple Users to LDAP | Completed |  | 2019-05-21 |  |  | ESS Job, paramter to be used: 'User Population' = 'All Users'
79 | Fusion | Version1 |  | Retrieve Latest LDAP Changes | Completed |  | 2019-05-21
80 | Fusion | Version1 | Madhu | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-21 | 17:00 - 18:00 | 60
81 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-21 | 14:00 - 18:00 | 240
Data Load - Day 10
82 | Fusion | Version1 | Madhu | Full load sanity testing prior to the termination run | Completed |  | 2019-05-21 | 9:00 - 11:00 | 120 | Manual activity using BI test SQL scripts
83 | Fusion | Version1 | Siva | Terminations | Completed | Completed | 2019-05-21 | 11:30 - 13:30 | 120 |  | 10978 | 10929 | 49 | 99.55 | 21157
84 | Fusion | Version1 |  | End/Set Inactive expired worker assignments | Completed | Completed | 2019-05-22 |  |  |  | 222 | 200 | 22 | 90.09 | 21163
84 | Fusion | Version1 | Madhu | Final Close date update for terminated workers | Completed | Completed | 2019-05-22 | 13:30 - 14:30 | 60 |  | 13716 | 13716 | 0 | 100
85 | Fusion | Version1 | Madhu/Siva | Log & Error Report Extraction/Analysis for the load completed | Completed |  | 2019-05-22 | 14:00 - 15:00 | 60 | Reports to be saved to secure drive location
86 | Fusion | Version1 | Natarajan | Reset the Worker auto numbering to enabled | Completed |  | 2019-05-22 | 15:30 - 15:45 | 15 | Manual Config update
87 | Fusion | Version1 | Natarajan | Reset the bank account encryption to enabled | Completed |  | 2019-05-22 | 15:45 - 16:00 | 15 | Manual Config update
88 | Fusion | Version1 | Natarajan/Subba | Data Reconciliation | Completed |  | 2019-05-22 | 14:00 - 18:00 | 240
89 | Fusion | Version1 | Kiran | Interim communication of Data Load completion (10 Days) | Completed |  | 2019-05-22 | 18:30 - 19:00 | 30 | Email communication
Data Load - Day 11
90 | Fusion | Version1 | Madhu | TimeCard calculation card data load for casuals | Not Started |  | 2019-05-25 | 9:00 - 11:00 | 120 |  |  |  | 0 | #DIV/0!
91 | Fusion | Version1 | Siva | Position EFF data load | Not Started | Not Started | 2019-05-25 | 11:30 - 13:30 | 120 |  |  |  | 0 | #DIV/0!
92 | Fusion | Version1 | Madhu | Final communication of Data Load completion | Not Started | Not Started | 2019-05-25 | 13:30 - 14:30 | 60
Note on E4: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E5: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E6: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E7: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E8: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E9: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E10: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E11: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E12: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E13: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on E14: Kiran Jagadeesan: Kiran Jagadeesan: Data loaded as part of the previous go live plan in Jan-2019, only incremental data to be loaded(if any) this time.
Note on I54: Kiran Jagadeesan: Program may be running approx. 9 hours, till early morning next day
Note on N86: Kiran Jagadeesan: 64 distinct workers failed (5 old MTM errors, others are part of manually entered workers)