## Version History
Maximise AT Roadmap - Version History
Date | Version | Description
2022-06-01 | 1.0 | Maximise DM Roadmap
2022-11-01 | 1.1 | Updated

## DM Roadmap v1_0
Maximise Data Migration Roadmap - 2022
| Q2-22 |  |  | Q3-22 |  |  | Q4-22
| Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Maximise Release
Outreach
Support
Reconciliation Reports
Backlog Development
BHC DM2 Support
Paratus Deployment
Maximise Release 22.2
Paratus Support
Backlog Development
Citco Support (DM1)
Backlog Development
Maximise Documentation
Maximise Commercial Model
Portal Updates
Portal Updates
Paratus Support
Backlog Development
Maximise Support
Backlog Development
Maximise Release 22.3
Citco Support (DM1)
Backlog Development
Maximise Documentation
Citco Lunch and Learn 22.1
BHC Maximise Demo
Cloud SA Team Quarterly Update
Mx Overview for Talent & Acquisition (part of T&I)
Mx Demo Transformation - BHC
Mx DM and AT Messaging - Sales/Pre-sales
Maximise DM and AT Release Update
Portal Updates
Implementation Estimate (Comm Model)
Setup Technical Working Group
Backlog Development
Backlog Development
Backlog Development
Maximise Release 22.4
Portal Updates
Implementation Estimate (Comm Model
Maximise DM and AT Release Update
Portal Updates
Backlog Prioritisation Q1-23 (TWG)
Implementation Estimate (Comm Model)

## DM Roadmap v2_0
Maximise Data Migration Roadmap - 2023
| Q1-23 |  |  | Q2-23 |  |  | Q3-23 |  |  | Q4-23
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Maximise Release
Outreach
Support
Maximise Commercial Model
Portal Updates
Portal Updates
Maximise Support
Citco Lunch and Learn 22.1
BHC Maximise Demo
Cloud SA Team Quarterly Update
Mx Overview for Talent & Acquisition (part of T&I)
Mx Demo Transformation - BHC
Mx DM and AT Messaging - Sales/Pre-sales
Maximise DM and AT Release Update
Portal Updates
Implementation Estimate (Comm Model)
Setup Technical Working Group
Portal Updates
Implementation Estimate (Comm Model
Maximise DM and AT Release Update
Portal Updates
Backlog Prioritisation Q1-23 (TWG)
Implementation Estimate (Comm Model)
Portal Updates
Implementation Estimate (Comm Model
Portal Updates
Implementation Estimate (Comm Model)
Setup Technical Working Group
Portal Updates
Implementation Estimate (Comm Model)
Setup Technical Working Group

## PK_Product Backlog_Plan
Product Development Roadmap
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec

## Sheet1
Team Breakup
Latheef | PLSQL
Ayush | PLSQL
Soundarya | OIC
Shireesha | OIC /VBCS
Pallavi | Support
Sinchana | Support

## Sheet2
Priority | Task | Feature Importance | Resource | Estimate | Start Date | Completion Date
1 | Installer improvements | Must Have | Latheef | 2 weeks | Jan | End Jan
1 | Training Videos | Must Have | Pallavi | 2 week | Jan | End Jan
1 | Improve HDL File Generation | Must Have | Ayush |  | Jan | March - First
1 | Error Handling Changes in OIC | Must Have | Latheef |  | Feb | Mar
1 | Ui to have the LOG table view on the Screen. | Must Have |  |  | Feb | May
1 | Smart Reconciliation | Nice to Have |  |  | March | End May
1 | Maximise Dashboard | Nice to Have | Shireesha |  |  | End Feb
1 | Batching HCM Testing | Must Have |  |  | Feb | End Feb
2 | PO Requisitions | Good to Have | Pallavi | 2 Weeks | Feb | End Feb
2 | Contract Purchase Orders | Good to Have | Sinchana | 1 week | Jan | End Jan
2 | Blanket Purchase Orders | Good to Have | Soundarya | 1 week | Jan | End Jan
2 | PO Receipts | Good to Have |  | 2 Weeks | March | March
2 | HR Locations | Good to Have |  | 2 Weeks | March | March
3 | Maximise Pre-validation Checks |  |  |  | Feb | April
3 | Review existing recon reports - Match with FBDI | Must Have |  |  | Feb | End March
3 | Maximise Transformation and Fusion Config Matching (Amit) | Nice to Have
4 | Configuration Automation | Nice to Have |  |  | March | End April
4 | Metadata Automation | Nice to Have |  |  | March | End April
4 | FBDI - Parameter Automation | Nice to Have |  |  | March | End April
4 | Fusion Error - Rerun | Must Have
4 | Ebs to Fusion - Configration Data Migration | Nice to Have
4 | Chatbot | Nice to Have
4 | Payroll
4 | Dechra - Maximise