## Validation Scripts
Validation Script Tracker
Business Entity | Sub Entity | Validation Status | Source Files Received in Citco gitlab | Validated Table | Validated Package | Tested Validations | Pushed to Cloudbridge Gitlab | Inlined with Cloudbridge Structure | Integrated in Cloudbridge | Integrated in Installation Document | Created By | Reviewed By | Work ETA | Comments
SUPPLIERS | SUPPLIERS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_ADDRESSES | SUPPLIER_ADDRESSES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_SITES | SUPPLIER_SITES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_SITES | SUPPLIER_THIRD_PARTY_RELS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_CONTACT | SUPPLIER_CONTACTS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_CONTACT | SUPPLIER_CONT_ADDRS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_SITE_ASSIGNS | SUPPLIER_SITE_ASSIGNS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_PAYEES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_BANK_ACCOUNTS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_PMT_INSTRS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
INVOICES | INVOICE_HEADERS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Husenabi/Harshith | Sinchana Ramesh |  | Completed
INVOICES | INVOICE_LINES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Husenabi/Harshith | Sinchana Ramesh |  | Completed
SUPPLIER_TAX | PARTY_TAX_PROFILE_CTL | 0 | [11 empty] | No Validation Scripts Developed
SUPPLIER_TAX | TAX_REGISTRATIONS | 0 | [11 empty] | No Validation Scripts Developed
CUSTOMERS | PARTIES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | PARTY_SITES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | PARTY_SITES_USES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | CUSTOMER_ACCOUNTS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | CUSTOMER_ACCOUNTS_SITES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | ACCOUNT_SITES_USES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | CUST_ACCT_RELATIONSHIPS | 0 | [8 empty] | Meenakshi | Shireesha TR |  | No Validation Scripts Developed
CUSTOMERS | CUST_ACCT_CONTACT | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | CONTACT_POINTS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | CONTACT_ROLES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | ORG_CONTACTS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | LOCATIONS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | RELATIONSHIPS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | ROLES_AND_RESPONSIBILITIES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | PARTY_CLASSIFICATIONS | 0 | [8 empty] | Meenakshi | Shireesha TR |  | No Validation Scripts Developed
CUSTOMERS | PERSON_LANGUAGE | 0 | [8 empty] | Meenakshi | Shireesha TR |  | No Validation Scripts Developed
CUSTOMERS | CUSTOMER_PROFILES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMERS | CUST_RECEIPT_METHODS | 0 | [8 empty] | Meenakshi | Shireesha TR |  | No Validation Scripts Developed
CUSTOMERS | CUST_BANKS | 0 | [8 empty] | Meenakshi | Shireesha TR |  | No Validation Scripts Developed
TRANSACTIONS | LINES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Husenabi/Harshith | Shireesha TR |  | Table's column are same as Cloudbridge and packages are working fine
TRANSACTIONS | DISTRIBUTIONS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Husenabi/Harshith | Shireesha TR
TRANSACTIONS | SALESCREDITS | 0 | [8 empty] | Husenabi/Harshith | Shireesha TR |  | Confirmed with Harshith - No validations were required for Salescredit
CASH_RECEIPTS | CASH_RECEIPTS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Husenabi/Harshith | Sinchana Ramesh |  | Completed
CUSTOMER_TAX | TAX_PROFILE | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Harshith JG | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMER_TAX | TAX_REGISTRATION | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Harshith JG | Shireesha TR |  | Testing is completed and it's working fine
CUSTOMER_TAX | PARTY_CLASSIFICATION | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Harshith JG | Shireesha TR |  | Testing is completed and it's working fine
OPEN_BAL | OPEN_BAL | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Shruti/Husenabi | Latheef Shaik |  | Completed
SUMM_BAL | SUMM_BAL | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Shruti/Husenabi | Latheef Shaik |  | Completed
DETAIL_BAL | DETAIL_BAL | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Shruti/Husenabi | Latheef Shaik |  | Completed
JOURNAL | JOURNAL | 0 | [11 empty] | No Validation Scripts Developed
DAILY_RATES | DAILY_RATES | 0 | [11 empty] | No Validation Scripts Developed
HISTORICAL_RATES | HISTORICAL_RATES | 0 | [11 empty] | No Validation Scripts Developed
FIXED_ASSETS | MASS_ADDITIONS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Sushma/Meenakshi | Latheef Shaik |  | Completed
FIXED_ASSETS | MASS_DISTRIBUTION | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Sushma/Meenakshi | Latheef Shaik |  | Completed
FIXED_ASSETS | MASS_RATES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Sushma/Meenakshi | Latheef Shaik |  | Completed
PURCHASE_ORDERS | PO_HEADERS_STD | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
PURCHASE_ORDERS | PO_LINES_STD | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
PURCHASE_ORDERS | PO_LINE_LOCATIONS_STD | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
PURCHASE_ORDERS | PO_DISTRIBUTIONS_STD | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Raghu/Meenakshi | Latheef Shaik |  | Completed
PURCHASE_ORDERS_BPA | PO_HEADERS_BPA | 0 | [11 empty] | No Validation Scripts Developed
PURCHASE_ORDERS_BPA | PO_LINES_BPA | 0 | [11 empty] | No Validation Scripts Developed
PURCHASE_ORDERS_BPA | PO_LINE_LOCATIONS_BPA | 0 | [11 empty] | No Validation Scripts Developed
PURCHASE_ORDERS_CPA | PO_HEADERS_CPA | 0 | [11 empty] | No Validation Scripts Developed
PURCHASE_ORDER_RECEIPT | PO_RECEIPT_HEADERS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Shruti/Husenabi | Sinchana Ramesh |  | Completed
PURCHASE_ORDER_RECEIPT | PO_RECEIPT_TRANSACTIONS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Shruti/Husenabi | Sinchana Ramesh |  | Completed
PRJ_FOUNDATION | PROJECTS | 1 | Y | [8 empty] | Latheef Shaik
PRJ_FOUNDATION | TASKS | 1 | Y | [8 empty] | Latheef Shaik
PRJ_FOUNDATION | TRX_CONTROL | 1 | Y | [8 empty] | Latheef Shaik
PRJ_FOUNDATION | TEAM_MEMBERS | 1 | Y | [8 empty] | Latheef Shaik
PRJ_FOUNDATION | CLASSIFICATIONS | 1 | Y | [8 empty] | Latheef Shaik
PRJ_RBS | RBS_HEADERS | 0 | [11 empty] | No Validation Scripts Developed
PRJ_RBS | RESOURCES | 0 | [11 empty] | No Validation Scripts Developed
PRJ_EVENTS | BILLING_EVENTS | 0 | [11 empty] | No Validation Scripts Developed
PRJ_COST | MISC_COSTS | 0 | [11 empty] | No Validation Scripts Developed
PRJ_COST | LABOUR_COST | 0 | [11 empty] | No Validation Scripts Developed
PRJ_COST | SUPPLIER_COST | 0 | [11 empty] | No Validation Scripts Developed
PRJ_COST | NON_LBR_COST | 0 | [11 empty] | No Validation Scripts Developed
BANKS_AND_BRANCHES | BANKS | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Veda/Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
BANKS_AND_BRANCHES | BANK_BRANCHES | 8 | Y | Y | Y | Y | Y | Y | Y | Y | Veda/Meenakshi | Shireesha TR |  | Testing is completed and it's working fine
?? | Employees | 0 | [8 empty] | Gaurav/Meenakshi |  |  | Business Entity not configured in Coudbridge
?? | Projects | 0 | [8 empty] | Gaurav/Meenakshi |  |  | Business Entity not configured in Coudbridge
?? | User Management | 0 | [8 empty] | Gaurav/Meenakshi |  |  | Business Entity not configured in Coudbridge
?? | Purchase Requisitions | 0 | [8 empty] | Shruti/Husenabi |  |  | Business Entity not configured in Coudbridge

## Code Comparison
Code Comparison Tracker
Business Entity | Sub Entity | Code Comparison Status | Source Files Received in Citco gitlab | Validated Package | Integrated with Cloudbridge | Tested in Cloudbridge | Pushed to Cloudbridge Gitlab | Created By | Reviewed By | Work ETA | Comments
SUPPLIERS | SUPPLIERS | 5 | Y | Y | Y | Y | Y | Veda/Amit | Ayush Rathore
SUPPLIER_ADDRESSES | SUPPLIER_ADDRESSES | 5 | Y | Y | Y | Y | Y | Veda/Amit | Ayush Rathore
SUPPLIER_SITES | SUPPLIER_SITES | 5 | Y | Y | Y | Y | Y | Veda/Amit | Ayush Rathore
SUPPLIER_SITES | SUPPLIER_THIRD_PARTY_RELS | 4 | Y | Y | Y | N | Y | Veda/Amit | Ayush Rathore |  | Changes done, but not tested due to unavailability of data
SUPPLIER_CONTACT | SUPPLIER_CONTACTS | 2 | Y | Y | N | N | N | Veda/Amit | Ayush Rathore |  | No need of any changes
SUPPLIER_CONTACT | SUPPLIER_CONT_ADDRS | 2 | Y | Y | N | N | N | Veda/Amit | Ayush Rathore |  | No need of any changes
SUPPLIER_SITE_ASSIGNS | SUPPLIER_SITE_ASSIGNS | 5 | Y | Y | Y | Y | Y | Veda/Amit | Ayush Rathore
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_PAYEES | 5 | Y | Y | Y | Y | Y | Veda/Amit | Ayush Rathore
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_BANK_ACCOUNTS | 2 | Y | Y | N | N | N | Veda/Amit | Ayush Rathore |  | No need of any changes
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_PMT_INSTRS | 2 | Y | Y | N | N | N | Veda/Amit | Ayush Rathore |  | No need of any changes
INVOICES | INVOICE_HEADERS | 0 | [8 empty] | Not in scope of Citco so no code been delivered
INVOICES | INVOICE_LINES | 0 | [8 empty] | Not in scope of Citco so no code been delivered
SUPPLIER_TAX | PARTY_TAX_PROFILE_CTL | 2 | Y | Y | N | N | N | Veda/Amit | Ayush Rathore |  | No need of any changes
SUPPLIER_TAX | TAX_REGISTRATIONS | 2 | Y | Y | N | N | N | Veda/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | PARTIES | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | PARTY_SITES | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | PARTY_SITES_USES | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | CUSTOMER_ACCOUNTS | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | CUSTOMER_ACCOUNTS_SITES | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | ACCOUNT_SITES_USES | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | CUST_ACCT_RELATIONSHIPS | 4 | Y | Y | Y | Y | N | Meenakshi/Amit | Ayush Rathore
CUSTOMERS | CUST_ACCT_CONTACT | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | CONTACT_POINTS | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | CONTACT_ROLES | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | ORG_CONTACTS | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | LOCATIONS | 2 | Y | Y | N | N | N | Meenakshi/Amit | Shireesha TR
CUSTOMERS | RELATIONSHIPS | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | ROLES_AND_RESPONSIBILITIES | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | PARTY_CLASSIFICATIONS | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | PERSON_LANGUAGE | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
CUSTOMERS | CUSTOMER_PROFILES | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Shireesha TR
CUSTOMERS | CUST_RECEIPT_METHODS | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Ayush Rathore
CUSTOMERS | CUST_BANKS | 2 | Y | Y | N | N | N | Meenakshi/Amit | Ayush Rathore |  | No need of any changes
TRANSACTIONS | LINES | 0 | [8 empty] | Not in scope of Citco so no code been delivered
TRANSACTIONS | DISTRIBUTIONS | 0 | [8 empty] | Not in scope of Citco so no code been delivered
TRANSACTIONS | SALESCREDITS | 0 | [8 empty] | Not in scope of Citco so no code been delivered
CASH_RECEIPTS | CASH_RECEIPTS | 1 | Y | N | N | N | N |  | Sinchana Ramesh
CUSTOMER_TAX | TAX_PROFILE | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Latheef Shaik
CUSTOMER_TAX | TAX_REGISTRATION | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Latheef Shaik
CUSTOMER_TAX | PARTY_CLASSIFICATION | 5 | Y | Y | Y | Y | Y | Meenakshi/Amit | Latheef Shaik
OPEN_BAL | OPEN_BAL | 5 | Y | Y | Y | Y | Y | Gaurav/Amit | Latheef Shaik
SUMM_BAL | SUMM_BAL | 5 | Y | Y | Y | Y | Y | Gaurav/Amit | Latheef Shaik
DETAIL_BAL | DETAIL_BAL | 5 | Y | Y | Y | Y | Y | Gaurav/Amit | Latheef Shaik
JOURNAL | JOURNAL | 0 | [8 empty] | Not in scope of Citco so no code been delivered
DAILY_RATES | DAILY_RATES | 5 | Y | Y | Y | Y | Y | Gaurav/Amit | Latheef Shaik
HISTORICAL_RATES | HISTORICAL_RATES | 5 | Y | Y | Y | Y | Y | Gaurav/Amit | Latheef Shaik
FIXED_ASSETS | MASS_ADDITIONS | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Latheef Shaik
FIXED_ASSETS | MASS_DISTRIBUTION | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Latheef Shaik
FIXED_ASSETS | MASS_RATES | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Latheef Shaik
PURCHASE_ORDERS | PO_HEADERS_STD | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Sinchana Ramesh
PURCHASE_ORDERS | PO_LINES_STD | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Sinchana Ramesh
PURCHASE_ORDERS | PO_LINE_LOCATIONS_STD | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Sinchana Ramesh
PURCHASE_ORDERS | PO_DISTRIBUTIONS_STD | 5 | Y | Y | Y | Y | Y | Sushma/Amit | Sinchana Ramesh
PURCHASE_ORDERS_BPA | PO_HEADERS_BPA | 0 | [8 empty] | Not in scope of Citco so no code been delivered
PURCHASE_ORDERS_BPA | PO_LINES_BPA | 0 | [8 empty] | Not in scope of Citco so no code been delivered
PURCHASE_ORDERS_BPA | PO_LINE_LOCATIONS_BPA | 0 | [8 empty] | Not in scope of Citco so no code been delivered
PURCHASE_ORDERS_CPA | PO_HEADERS_CPA | 0 | [8 empty] | Not in scope of Citco so no code been delivered
PURCHASE_ORDER_RECEIPT | PO_RECEIPT_HEADERS | 0 | [8 empty] | Not in scope of Citco so no code been delivered
PURCHASE_ORDER_RECEIPT | PO_RECEIPT_TRANSACTIONS | 0 | [8 empty] | Not in scope of Citco so no code been delivered
PRJ_FOUNDATION | PROJECTS | 2 | Y | Y | N | N | N |  | Shaik Latheef
PRJ_FOUNDATION | TASKS | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_FOUNDATION | TRX_CONTROL | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_FOUNDATION | TEAM_MEMBERS | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_FOUNDATION | CLASSIFICATIONS | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_RBS | RBS_HEADERS | 0 | [6 empty] | Sinchana Ramesh |  | Not in scope of Citco so no code been delivered
PRJ_RBS | RESOURCES | 0 | [6 empty] | Sinchana Ramesh |  | Not in scope of Citco so no code been delivered
PRJ_EVENTS | BILLING_EVENTS | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_COST | MISC_COSTS | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_COST | LABOUR_COST | 2 | Y | Y | N | N | N |  | Sinchana Ramesh
PRJ_COST | SUPPLIER_COST | 0 | [6 empty] | Sinchana Ramesh |  | Not in scope of Citco so no code been delivered
PRJ_COST | NON_LBR_COST | 0 | [6 empty] | Sinchana Ramesh |  | Not in scope of Citco so no code been delivered
BANKS_AND_BRANCHES | BANKS | 4 | Y | Y | Y | N | Y | Veda/Amit | Ayush Rathore |  | Changes done, but could not test
BANKS_AND_BRANCHES | BANK_BRANCHES | 4 | Y | Y | Y | N | Y | Veda/Amit | Ayush Rathore |  | Changes done, but could not test
?? | Employees | 0 | [8 empty] | Business Entity not configured in Coudbridge
?? | Projects | 0 | [8 empty] | Business Entity not configured in Coudbridge
?? | User Management | 0 | [8 empty] | Business Entity not configured in Coudbridge
?? | Purchase Requisitions | 0 | [8 empty] | Business Entity not configured in Coudbridge

## BIP Reports
BIP Reports Comparison Tracker
Business Entity | Sub Entity | Report Comparison Status | Report Received in Citco gitlab | Validated Report | Document Developed | Integrated with Cloudbridge | Tested in Cloudbridge | Pushed to Cloudbridge Gitlab | Created By | Reviewed By | Work ETA | Comments
SUPPLIERS | SUPPLIERS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
SUPPLIER_ADDRESSES | SUPPLIER_ADDRESSES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
SUPPLIER_SITES | SUPPLIER_SITES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
SUPPLIER_SITES | SUPPLIER_THIRD_PARTY_RELS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
SUPPLIER_CONTACT | SUPPLIER_CONTACTS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created, No changes identied
SUPPLIER_CONTACT | SUPPLIER_CONT_ADDRS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created, No changes identied
SUPPLIER_SITE_ASSIGNS | SUPPLIER_SITE_ASSIGNS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_PAYEES | 1 | Y | N | N | N | N | N | Ayush Rathore |  |  | Not found in Maximise
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_BANK_ACCOUNTS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
SUPPLIER_BANK_ACCOUNTS | SUPPLIER_PMT_INSTRS | 1 | Y | N | N | N | N | N | Ayush Rathore |  |  | Not found in Maximise
INVOICES | INVOICE_HEADERS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created, No changes identied
INVOICES | INVOICE_LINES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created, No changes identied
SUPPLIER_TAX | PARTY_TAX_PROFILE_CTL | 1 | Y | N | N | N | N | N | Ayush Rathore |  |  | Not found in Maximise
SUPPLIER_TAX | TAX_REGISTRATIONS | 1 | Y | N | N | N | N | N | Ayush Rathore |  |  | Not found in Maximise
CUSTOMERS | PARTIES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | PARTY_SITES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | PARTY_SITES_USES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | CUSTOMER_ACCOUNTS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | CUSTOMER_ACCOUNTS_SITES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | ACCOUNT_SITES_USES | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | CUST_ACCT_RELATIONSHIPS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | CUST_ACCT_CONTACT | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | CONTACT_POINTS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | CONTACT_ROLES | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | ORG_CONTACTS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | LOCATIONS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
CUSTOMERS | RELATIONSHIPS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | ROLES_AND_RESPONSIBILITIES | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | PARTY_CLASSIFICATIONS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | PERSON_LANGUAGE | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Citco has not developed report, confirmed with meenakshi
CUSTOMERS | CUSTOMER_PROFILES | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMERS | CUST_RECEIPT_METHODS | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Citco has not developed report, confirmed with meenakshi
CUSTOMERS | CUST_BANKS | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Citco has not developed report, confirmed with meenakshi
TRANSACTIONS | LINES | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
TRANSACTIONS | DISTRIBUTIONS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
TRANSACTIONS | SALESCREDITS | 1 | Y | N | N | N | N | N | Sinchana Ramesh |  |  | Report not available in maximise
CASH_RECEIPTS | CASH_RECEIPTS | 1 | Y | N | N | N | N | N | Sinchana Ramesh |  |  | Report not available in maximise
CUSTOMER_TAX | TAX_PROFILE | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMER_TAX | TAX_REGISTRATION | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
CUSTOMER_TAX | PARTY_CLASSIFICATION | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
OPEN_BAL | OPEN_BAL | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
SUMM_BAL | SUMM_BAL | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
DETAIL_BAL | DETAIL_BAL | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh
JOURNAL | JOURNAL | 0 | N | N | N | N | N | N | Sinchana Ramesh
DAILY_RATES | DAILY_RATES | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh
HISTORICAL_RATES | HISTORICAL_RATES | 2 | Y | N | Y | N | N | N | Sinchana Ramesh
FIXED_ASSETS | MASS_ADDITIONS | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
FIXED_ASSETS | MASS_DISTRIBUTION | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
FIXED_ASSETS | MASS_RATES | 1 | Y | N | N | N | N | N | Ayush Rathore |  |  | Not found in Maximise
PURCHASE_ORDERS | PO_HEADERS_STD | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
PURCHASE_ORDERS | PO_LINES_STD | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
PURCHASE_ORDERS | PO_LINE_LOCATIONS_STD | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
PURCHASE_ORDERS | PO_DISTRIBUTIONS_STD | 3 | Y | Y | Y | N | N | N | Ayush Rathore |  |  | Comparison Document Created
PURCHASE_ORDERS_BPA | PO_HEADERS_BPA | 0 | N | N | N | N | N | N | Ayush Rathore |  |  | Reports not available in Citco & Maximise
PURCHASE_ORDERS_BPA | PO_LINES_BPA | 0 | N | N | N | N | N | N | Ayush Rathore |  |  | Reports not available in Citco & Maximise
PURCHASE_ORDERS_BPA | PO_LINE_LOCATIONS_BPA | 0 | N | N | N | N | N | N | Ayush Rathore |  |  | Reports not available in Citco & Maximise
PURCHASE_ORDERS_CPA | PO_HEADERS_CPA | 0 | N | N | N | N | N | N | Ayush Rathore |  |  | Reports not available in Citco & Maximise
PURCHASE_ORDER_RECEIPT | PO_RECEIPT_HEADERS | 0 | N | N | N | N | N | N | Ayush Rathore |  |  | Reports not available in Citco
PURCHASE_ORDER_RECEIPT | PO_RECEIPT_TRANSACTIONS | 0 | N | N | N | N | N | N | Ayush Rathore |  |  | Reports not available in Citco
PRJ_FOUNDATION | PROJECTS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PRJ_FOUNDATION | TASKS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PRJ_FOUNDATION | TRX_CONTROL | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PRJ_FOUNDATION | TEAM_MEMBERS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PRJ_FOUNDATION | CLASSIFICATIONS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PRJ_RBS | RBS_HEADERS | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
PRJ_RBS | RESOURCES | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
PRJ_EVENTS | BILLING_EVENTS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PRJ_COST | MISC_COSTS | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
PRJ_COST | LABOUR_COST | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
PRJ_COST | SUPPLIER_COST | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
PRJ_COST | NON_LBR_COST | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
BANKS_AND_BRANCHES | BANKS | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
BANKS_AND_BRANCHES | BANK_BRANCHES | 0 | N | N | N | N | N | N | Sinchana Ramesh |  |  | Reports not available
?? | Employees | 0
?? | Projects | 0
?? | User Management | 0
?? | Purchase Requisitions | 0
WORKER | Worker Assignment | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Worker Measure | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Assignment Payroll | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Assignment Supervisor | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | External bank account | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Assignment grade step | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Assignment salary | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Person payment method | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Person workreleationship | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Worker(POS) | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
WORKER | Term assignment | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person NID | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Address | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Name | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Religion | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Disability | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Legislative | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Ethnicity | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Phone | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person citizenships | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person email | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person Image | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person visa | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person passport | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Contact releationships | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Contact address | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Contact phone | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Contact name | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person contact | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
PERSON | Person absence/mat absence | 3 | Y | Y | Y | N | N | N | Sinchana Ramesh |  |  | Comparison Document Created
USERS | User data access | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
USERS | User employees | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
USERS | User accounts for employees | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
USERS | Users role in cloud | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
LEARNING | Learner Records | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
LEARNING | Specialization | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Billing events against contracts | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract number lines | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract Bill Plans | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract ID Number | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract Amount | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contracts | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract Party | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract Party Contact | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Associated Projects | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
CONTRACTS | Contract Status | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
RECRUITMENT | Candidates Attachments | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
RECRUITMENT | Candidates Attachments | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
RECRUITMENT | Job Requistion | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
RECRUITMENT | Model Profile Desc | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
RECRUITMENT | Only Candidates | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
PPM - INVOICES | Invoice Num_Id | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise
PPM - INVOICES | Invoice | 5 | Y | Y | Y | Y | Y | N | Sinchana Ramesh |  |  | Entity not present in maximise. Integrated it to maximise

## Sheet1
SUPPLIER_THIRD_PARTY_RELS
SUPPLIER_CONTACTS
SUPPLIER_CONT_ADDRS
PARTY_TAX_PROFILE_CTL
TAX_REGISTRATIONS

## Issues
Sub Entity | Issue | Error