## WorkCycle 11
Sprint 11 | Epic/Feature | Product Backlog item | Status | Task | Estimate(days) | Resource
| Maximise Dashboard | Adding Start time and end time for Extract, Transform and Import | Completed | Adding start time and end time for Import- integration changes and testing | 2 | Shireesha
|  |  | Completed | VBCS configuration to display start time and end time column for Import (end date)and testing-BIP Report | 3 | Shireesha
| Maximise Dashboard | Adding Start time and end time for Extract, Transform and Import | In Progress | Issue where count where 0 | 1 | Shireesha
| Maximise Dashboard | Integration of Error and Success Report for Suppliers | Completed | Integration of Error and Success Report for SUPPLIER_ADDRESS | 2 | Ayush
|  |  | Completed | Integration of Error and Success Report for SUPPLIER_SITE | 2 | Shireesha
| Maximise Dashboard | Integration of Error and Success Report for Suppliers | In Progress | Integration of Error and Success Report for SUPPLIER_SITE_ASSIGNMENTS | 2 | Ayush
|  |  | Completed | Integration of Error and Success Report for THIRD PARTY RELATIONSHIP | 2 | Shireesha
| Maximise Dashboard | Integration of Error and Success Report for Suppliers | In Progress | Integration of Error and Success Report for SUPPILER_CONTACTS | 2 | Ayush
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | Completed | Test GetLoadNameScope | 0.2 | Ayush
|  |  | Completed | Test GetParamValuesScope | 0.2 | Ayush
|  |  | Completed | Test GetESSConstantsScope | 0.2 | Ayush
|  |  | Completed | Test GetBUIdsScope | 0.2 | Ayush
|  |  | Completed | Test GetLedgerIdScope | 0.2 | Ayush
|  |  | Completed | Test GetAssetBookNameScope | 0.2 | Ayush
|  |  | Completed | Test GetDASRecordsScope | 0.2 | Ayush
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | InProgress | Test ImportARICInvoicesScope | 0.2 | Latheef
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | InProgress | Test ImportProjectCostsScope | 0.2 | Latheef
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | InProgress | Test ImportProjectsScope | 0.2 | Latheef
|  |  | Completed | Test ImportCustomersScope | 0.2 | Latheef
|  |  | Completed | Test ImportSuppliersScope | 0.2 | Ayush
|  |  | Completed | Test ImportSupplierAddressesScope | 0.2 | Ayush
|  |  | Completed | Test ImportSupplierSitesScope | 0.2 | Ayush
|  |  | Completed | Test ImportSupplierSiteAssignmentsScope | 0.2 | Ayush
|  |  | Completed | Test ImportSupplierContactsScope | 0.2 | Ayush
|  |  | Completed | Test ImportSupplierBankAccountsScope | 0.2 | Ayush
|  |  | Completed | Test ImportBPAScope | 0.2 | Latheef
|  |  | Completed | Test ImportCPAScope | 0.2 | Latheef
|  |  | Completed | Test ImportAPInvoicesScope | 0.2 | Ayush
|  |  | Completed | Test ImportFixedAssetsScope | 0.2 | Ayush
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | InProgress | Test ImportARInvoicesScope | 0.2 | Latheef
|  |  | Completed | Test ImportTrailBalanceScope | 0.2 | Latheef
|  |  | Completed | Test ImportOrdersScope | 0.2 | Latheef
|  |  | Completed | Test ListFilesScope | 0.2 | Latheef
|  |  | Completed | Test DownloadFilesScope | 0.2 | Latheef
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | InProgress | Test CallHCMLoaderScope | 0.2 | Latheef
|  |  | Completed | Test ImportDailyRatesScope | 0.2 | Latheef
|  |  | Completed | Test GetOpenBalScope | 0.2 | Latheef
|  |  | Completed | Test ImportOpenBalScope | 0.2 | Latheef
|  |  | Completed | Test GetSummaryBalScope | 0.2 | Latheef
|  |  | Completed | Test ImpSumBalScope | 0.2 | Latheef
|  |  | Completed | Test GetDetailBalScope | 0.2 | Latheef
|  |  | Completed | Test ImportDetailsBalScope | 0.2 | Latheef
|  |  | Completed | Test ImportSupplierThirdPartyPaymentRelationshipsScope | 0.2 | Latheef
|  |  | Completed | Test ImportSupplierContactAddressesScope | 0.2 | Latheef
|  |  | Completed | Test ImportSupplierPayeesScope | 0.2 | Latheef
|  |  | Completed | Test GetHistoricalRatesScope | 0.2 | Latheef
|  |  | Completed | Test ImportHistoricalRatesScope | 0.2 | Latheef
| Maximise Dashboard | Merge pages with Dashboard | Completed | Merge Extract Page | 0.5 | Latheef
|  |  | Completed | Merge Upload STG Page | 0.5 | Latheef
|  |  | Completed | Merge Transform Page | 0.5 | Latheef
|  |  | Completed | Merge Upload XFM Page | 0.5 | Latheef
|  |  | Completed | Merge Load File Generation Page | 0.5 | Latheef
|  |  | Completed | Merge Load Files Page | 0.5 | Latheef
|  |  | Completed | Merge Import Page | 0.5 | Latheef
| Maximise Dashboard | Import: Loading and Importing for Purchase Order for success records | Completed | PO Headers -Data Model Creation | 0.5 | Sinchana
| Maximise Dashboard | Import: Loading and Importing for Purchase Order for success records | InProgress | PO Distributions-Data Model Creation | 0.5
|  |  | Completed | PO Lines-Data Model Creation | 0.5
|  |  | Completed | PO Line Locations-Data Model Creation | 0.5
|  |  | Completed | PO Headers -Report Creation | 0.5
| Maximise Dashboard | Import: Loading and Importing for Purchase Order for success records | InProgress | PO Distributions-Report Creation | 0.5
|  |  | Completed | PO Lines-Report Creation | 0.5
|  |  | Completed | PO Line Locations-Report Creation | 0.5
| Maximise Dashboard | Creation of Report for AP Invoices | Completed | Creation of Report for Success data for data model(Counts and Detail) | 0.5 | Sinchana
|  |  | Completed | Creation of Data Model for Success data for data model(Counts and Detail) | 0.5
| Maximise Dashboard | Creation of Report for Supplier Bank PAYEES | Completed | Creation of Data model for Success data (Counts and Detail) | 0.5 | Sinchana
|  |  | Completed | Creation of Report for Success data for data model(Counts and Detail) | 0.5
| Maximise Dashboard | Creation of Report for r Supplier Bank Accounts | Completed | Creation of Data Model for Success data for data model(Counts and Detail) | 0.5 | Sinchana
|  |  | Completed | Creation of Report for Success data for data model(Counts and Detail) | 0.5
| Maximise Dashboard | Creation of Success Reports Customers |  |  |  | Soundarya
|  |  | Completed | Creation of Data Model for Success data PARTIES | 0.5
|  |  | Completed | Creation of Report for Success dataPARTIES | 0.5
|  |  | Completed | Creation of Data Model for Success data PARTY SITES | 0.5
|  |  | Completed | Creation of Report for Success data PARTY SITES | 0.5
|  |  | Completed | Creation of Data Model for Success data PARTY SITE USES | 0.5
|  |  | Completed | Creation of Report for Success data PARTY SITE USES | 0.5
|  |  | Completed | Creation of Data Model for Success data CUSTOMER ACCOUNTS | 0.5
|  |  | Completed | Creation of Report for Success data CUSTOMER ACCOUNTS | 0.5
|  |  | Completed | Creation of Data Model for Success data CUSTOMER ACCOUNT SITES | 0.5
|  |  | Completed | Creation of Report for Success data CUSTOMER ACCOUNT SITES | 0.5
| Maximise Dashboard | Creation of Success Reports Customers | InProgress | Creation of Data Model for Success data CUSTOMER ACCOUNT SITE USES | 0.5
| Maximise Dashboard | Creation of Success Reports Customers | InProgress | Creation of Report for Success data CUSTOMER ACCOUNT SITE USES | 0.5
| Maximise Dashboard | Creation of Report for Supplier Payment Instruction |  |  |  | Soundarya
| Maximise Dashboard | Creation of Report for Supplier Payment Instruction | InProgress | Creation of DataModel for Success data for data model(Counts and Detail) | 0.5
| Maximise Dashboard | Creation of Report for Supplier Payment Instruction | InProgress | Creation of Report for Success data for data model(Counts and Detail) | 0.5

## WorkCycle 12
Sprint 11
Old Sprint | Epic/Feature | Product Backlog item |  | Task | Estimate | Assigned To | Reviewed By
| Maximise Dashboard | Success Reports for Customers Part1 |  | Creation of Data Model CUSTOMER ACCOUNT RELATIONSHIPS | 0.5 | Sinchana | Ayush
|  |  |  | Creation of Report CUSTOMER ACCOUNT RELATIONSHIPS | 0.5 | Sinchana | Ayush
|  |  |  | Creation of Data Model CUSTOMER ACCOUNT CONTACTS | 0.5 | Sinchana | Ayush
|  |  |  | Creation of Report CUSTOMER ACCOUNT CONTACTS | 0.5 | Sinchana | Ayush
|  |  |  | Creation of Data Model CONTACT POINTS | 0.5 | Sinchana | Shireesha
|  |  |  | Creation of Report CONTACT POINTS | 0.5 | Sinchana | Shireesha
|  |  |  | Creation of Data Model CONTACT ROLES | 0.5 | Sinchana | Shireesha
|  |  |  | Creation of Report CONTACT ROLES | 0.5 | Sinchana | Shireesha
|  |  |  | Creation of Data Model CUSTOMER RECEIPT METHODS | 0.5 | Sinchana | Soundarya
|  |  |  | Creation of Reports CUSTOMER RECEIPT METHODS | 0.5 | Sinchana | Soundarya
|  |  |  | Creation of Data Model CUSTOMER BANK ACCOUNTS | 0.5 | Sinchana | Soundarya
|  |  |  | Creation of Reports CUSTOMER BANK ACCOUNTS | 0.5 | Sinchana | Soundarya
|  |  |  | Creation of Data Model PERSON LANGUAGES | 0.5 | Sinchana | Soundarya
|  |  |  | Creation of Reports PERSON LANGUAGES | 0.5 | Sinchana | Soundarya
| Maximise Dashboard | Success Reports for Customers Part2 |  | Creation of Data Model CONTACTS | 0.5 | Soundarya | Shireesha
|  |  |  | Creation of Report CONTACTS | 0.5 | Soundarya | Shireesha
|  |  |  | Creation of Data Model LOCATIONS | 0.5 | Soundarya | Latheef
|  |  |  | Creation of Report LOCATIONS | 0.5 | Soundarya | Latheef
|  |  |  | Creation of Data Model PARTY RELATIONSHIPS | 0.5 | Soundarya | Sinchana
|  |  |  | Creation of Report PARTY RELATIONSHIPS | 0.5 | Soundarya | Sinchana
|  |  |  | Creation of Data Model PARTY ROLE RESPONSIBILITIES | 0.5 | Soundarya | Shireesha
|  |  |  | Creation of Report PARTY ROLE RESPONSIBILITIES | 0.5 | Soundarya | Shireesha
|  |  |  | Creation of Data Model CLASSIFICATIONS | 0.5 | Soundarya | Sinchana
|  |  |  | Creation of Report CLASSIFICATIONS | 0.5 | Soundarya | Sinchana
|  |  |  | Creation of Data Model CUSTOMER PROFILES | 0.5 | Soundarya | Sinchana
|  |  |  | Creation of Reports CUSTOMER PROFILES | 0.5 | Soundarya | Sinchana
| Maximise Dashboard | Adding graph/ chart for Counts | In Progress | Researching on graphs or charts in vbcs to know how it works | 3 | shireesha | Ayush
|  |  |  | Adding the bar graph in vbcs dashboard page | 1 | shireesha | Ayush
| HCM Inline with FIN | VBCS Changes for HCM |  | Adding FileName in Load tile | 1.5 | Ayush | Latheef
|  |  |  | Adding DB Object, Types and Variables, Endpoints | 1.5 | Ayush | Latheef
|  |  |  | Adding data into the lookups | 1.5 | Ayush | Latheef
|  |  |  | logic to enable File Name when application suite HCM is selected | 2 | Ayush | Latheef
| Maximise Dashboard | Integration of Error and Success Report for AP_INVOICES
|  |  |  | Integration of Error Report for AP_INVOICES _LINES_INTERFACE | 1.5 | Shireesha | Soundarya/Latheef
|  |  |  | Integration of Error Report for AP_INVOICES_INTERFACE | 1.5 | Shireesha | Soundarya/Latheef
Sprint 10
| Maximise Dashboard | Adding Start time and end time for Extract, Transform and Import | Completed | Issue where count where 0 | 1 | Shireesha | Ayush
| Maximise Dashboard | Integration of Error and Success Report for Suppliers | Review | Integration of Error and Success Report for SUPPLIER_SITE_ASSIGNMENTS | 0.5 | Ayush | Shireesha
Move it to new PBI | Maximise Dashboard | Integration of Error and Success Report for Supplier Contact | In Progress | Integration of Error and Success Report for SUPPILER_CONTACTS | 2 | Ayush | Sinchana/Shireesha
Move it to new PBI | Maximise Dashboard | Integration of Error and Success Report for Supplier Contact |  | Integration of Error and Success Report for SUPPILER_CONTACT_ADDRESS | 2 | Ayush | Sinchana/Shireesha
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | Completed | Test ImportARICInvoicesScope | 0.2 | Latheef
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | Completed | Test ImportProjectCostsScope | 0.2 | Latheef
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | Completed | Test ImportProjectsScope | 0.2 | Latheef
| Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process | Completed | Test ImportARInvoicesScope | 0.2 | Latheef
Move it new PBI | Maximise Dashboard | Import: Loading and Importing for Purchase Order Distribution for success records | In Progress | PO Distributions-Data Model Creation | 0.5 | Sinchana | Latheef
Move it new PBI | Maximise Dashboard | Import: Loading and Importing for Purchase Order Distribution for success records | In Progress | PO Distributions-Report Creation | 0.5 | Sinchana | Latheef
| Maximise Dashboard | Creation of Success Reports Customers | Completed | Creation of Data Model for Success data CUSTOMER ACCOUNT SITE USES | 0.5 | Soundarya | Shireesha
| Maximise Dashboard | Creation of Success Reports Customers | Completed | Creation of Report for Success data CUSTOMER ACCOUNT SITE USES | 0.5 | Soundarya | Shireesha
| Maximise Dashboard | Creation of Report for Supplier Payment Instruction |  | Creation of DataModel for Success data for data model(Counts and Detail) | 0.5 | Soundarya | Latheef
| Maximise Dashboard | Creation of Report for Supplier Payment Instruction |  | Creation of Report for Success data for data model(Counts and Detail) | 0.5 | Soundarya | Latheef
Move it new PBI | Enhanced Error Handling | INTDM999007 DM Run Fusion Import Process- HCM Load Scope |  | Test CallHCMLoaderScope | 3 | Latheef | Ayush
| Enhanced Error Handling | VBCS Screen Changes | In Progress | Disable the submit Button on Maximise VBCS | 1.5 | Latheef | Ayush
| Smart Reconciliation | Apex Functionality Analysis |  | APEX Analysis | 2 | Latheef
| Enhanced Error Handling | VBCS Screen Changes | In Progress | Field Refresh on VBCS , Adding new Business Objects in lookup | 1.5 | Latheef

## WorkCycle 13
Sprint 13
Old Sprint | Epic/Feature | Product Backlog item | Priority - Task | Task | Estimate | Assigned To | Reviewed By
| HCM Inline with FIN | Creation of Proc WorkRelationship | 1 | Build procedure | 4 | Ayush | Latheef
|  |  | 1 | STG table creation | 1.5 | Ayush | Latheef
|  |  | 1 | XFM table creation | 1.5 | Ayush | Latheef
|  |  | 1 | Changes in extract package | 2 | Ayush | Latheef
|  | HCM Load File generation | 2 | Modifying File name logic | 1 | Ayush | Soundarya
|  |  | 2 | Testing files : WorkerHire,PersonalPaymentMethod,WorkerSupervisor,ExternalBankAccount | 2 | Ayush | Soundarya
|  |  | 2 | Testing files: WorkerCurrent,WorkerTermination | 2 | Ayush | Soundarya
| Smart Reconciliation | Apex POC on Suppliers |  | Explore Apex | 2 | Latheef | Pallavi/Praveen
|  |  |  | POC on Apex | 3 | Latheef | Pallavi/Praveen
| Maximise Dashboard | To display Graph data in Dashboard page |  | Populating and configuring to display Graph data | 3 | Shireesha | Pallavi/Praveen
|  |  |  | Testing the working of Graph | 1 | Shireesha | Pallavi/Praveen
| Creation of Data model for GL | Creation of Success Data model for General Ledger( Import Journals) |  | Discussion with Husenabi for General Ledger Success Reports |  | Soundarya | Sinchana
|  |  |  | Count Report creation for GL Journals | 1 | Soundarya | Sinchana
|  |  |  | Detail Report creation for GL Journals | 1 | Soundarya | Sinchana
| Customer Batch Id creation | Working on customers Batch_id creation |  | Changing the table structure for Customer Tables XFM and STG | 2 | Soundarya | Ayush
|  |  |  | Package changes to create Batch ID | 2 | Soundarya | Latheef
|  |  |  | Testing the batchid | 1 | Soundarya | Ayush
| Maximise Dashboard | Integration of Error and Success Report for Suppliers |  | Integration of Error and Success Report for SUPPLIER_PAYEE | 3 | Sinchana | Ayush
|  | Integration of Error and Success Report for Suppliers |  | Integration of Error and Success Report for SUPPILER_BANKS | 3 | Sinchana | Ayush
|  | Integration of Error and Success Report for Suppliers |  | Integration of Error and Success Report for SUPPILER_PAYMENT_INSTRUMENTS | 3 | Sinchana | Ayush

## WorkCycle 14
Sprint 14
Old Sprint | Epic/Feature | Product Backlog item | Priority - Task | Task | Estimate | Assigned To | Reviewed By
Start from 22 May | PO Receipts | PO Receipts Package Creation | 2 | Procedure for PO Receipts Header | 3 | Sinchana | Ayush
|  |  | 2 | Testing PO Receipts Headers | 2 | Sinchana | Ayush
Start from 16th May | HCM Load File generation | Modifying Zip File name logic |  | Modifying the zip file name logic to make the load file more readable. | 1 | Ayush | Soundarya
|  | Testing files : WorkerHire,PersonalPaymentMethod,WorkerSupervisor,ExternalBankAccount |  | Running and testing the load for mentioned FileName | 2 | Ayush | Soundarya
|  | Testing files : WorkerAddAsg,PersonImages,PersonMaternityAbsenceEntry,PersonAbsenceEntry |  | Running and testing the load for mentioned FileName | 2 | Ayush | Soundarya
|  | Testing files: WorkerCurrent,WorkerTermination |  | Running and testing the load for mentioned FileName | 2 | Ayush | Soundarya
| HCM Load file folder structure change | HCM Load file folder structure change |  | HCM Load file folder structure change | 3 | Ayush | Sinchana
Start from 16th May | HR Locations | HR Location Configuration |  | Staging table , XFM table Creation | 2 | Soundarya | Latheef
|  | HR Location Configuration |  | Metadata and Data Dictionary | 2 | Soundarya | Latheef
|  | HR Location Extract Package Creation |  | Extract Package Creation | 5 | Soundarya | Latheef
| HR Locations Extract Testing | HR Location Extract Package Creation |  | Testing the E2E flow | 1 | Soundarya | Latheef
Start from 22 May | Maximise Dashboard | Integration of Error and Success Report for Fixed Assets Mass Additions | 2 | Integration of Error and Success Report for Fixed Assets Mass Additions | 2 | Shireesha | Sinchana
|  | Integration of Error and Success Report for Fixed Assets Mass Distributions | 2 | Integration of Error and Success Report for Fixed Assets Mass Distributions | 2 | Shireesha | Sinchana
|  | Integration of Error and Success Report for Fixed Assets Mass Rates | 2 | Integration of Error and Success Report for Fixed Assets Mass Rates | 1 | Shireesha | Sinchana
Start from 16th May | Maximise Dashboard | Integration of Error and Success Report for PO Line Locations | 1 | Integration of Error and Success Report for PO Line Locations | 2 | Sinchana | Shireesha
|  | Integration of Error and Success Report for PO Distributions | 1 | Integration of Error and Success Report for PO Distributions | 2 | Sinchana | Shireesha
|  | Review | 1 | Review | 1 | Sinchana | Shireesha
Start from 16th May | Bug fix on Maximise Dashboard | To fix the error on Scheduled integration | 1 | To fix the error on Scheduled integration | 2 | Shireesha | Ayush
Start from 16th May | Maximise Dashboard | To make the time from all environments(Fusion,OIC,SQL database) to a single timezone | 1 | Analyse the logic to get the time from all environment to a single timezone | 1 | Shireesha | Ayush
|  |  | 1 | Implement logic to get the time from all environment to a single timezone | 2 | Shireesha | Ayush
Start from 16th May | Smart Reconciliation | Link Python with Maximise Database |  | Connecting with Python with Database using Anaconda | 3 | Latheef | Shireesha
|  | POC for Supplier SubEntity Reconciliation |  | POC for Supplier SubEntity Reconciliation | 7 | Latheef | Shireesha

## Report Status
BUSSINESS_ENTITY | SUB_ENTITY | ERROR_REPORTS | SUCCESS_REPORT
SUPPLIER | SUPPLIER | YES | YES
| SUPPLIER_ADDRESS | YES | YES
| SUPPLIER_SITE | YES | YES
| SUPPLIER_SITE_ASSIGNMENTS | YES | YES
| THIRD PARTY RELATIONSHIP | YES | YES
SUPPLIER_CONTACTS | SUPPILER_CONTACTS | YES | YES
| SUPPLIER_CONTACT_ADDRESS | YES | YES
SUPPLIER BANK | SUPPLIER BANK ACCOUNTS | YES | YES
| SUPPLIER BANK PAYEES | YES | IN PROGRESS | Sprint 12
| SUPPLIER EXTERNAL PAYMENT INSTRUCTIONS | YES | YES
AP_INVOICES | AP_INVOICES INTERFACE | YES | YES
| AP_INVOICES _LINES_INTERFACE | YES | YES
CUSTOMER | PARTIES | YES | YES
| PARTY SITES | YES | YES
| PARTY SITE USES | YES | YES
| CUSTOMER ACCOUNTS | YES | YES
| CUSTOMER ACCOUNT SITES | YES | YES
| CUSTOMER ACCOUNT SITE USES | YES | IN PROGRESS | Sprint 12
| CUSTOMER ACCOUNT RELATIONSHIPS | YES | IN PROGRESS | Sprint 12
| CUSTOMER ACCOUNT CONTACTS | YES | IN PROGRESS | Sprint 12
| CONTACT POINTS | YES | IN PROGRESS | Sprint 12
| CONTACT ROLES | YES | IN PROGRESS | Sprint 12
| CONTACTS | YES | IN PROGRESS | Sprint 12
| LOCATIONS | YES | IN PROGRESS | Sprint 12
| PARTY RELATIONSHIPS | YES | IN PROGRESS | Sprint 12
| PARTY ROLE RESPONSIBILITIES | YES | IN PROGRESS | Sprint 12
| CLASSIFICATIONS | YES | IN PROGRESS | Sprint 12
| PERSON LANGUAGES | YES | IN PROGRESS | Sprint 12
| CUSTOMER PROFILES | YES | IN PROGRESS | Sprint 12
| CUSTOMER RECEIPT METHODS | YES | IN PROGRESS | Sprint 12
| CUSTOMER BANK ACCOUNTS | YES | IN PROGRESS | Sprint 12
FIXED ASSETS | ADDITIONS | YES | YES
| DISTRIBUTIONS | YES | YES
| RATES | YES | YES
GENERAL LEDGER | Journal Import/ Balances | YES | IN PROGRESS
| Daily Rates | YES
| Historical Rates | YES
PROJECTS | PROJECTS | YES
| TASKS | YES
| TRANSACTION CONTROLS | YES
| PROJECT TEAM MEMBERS | YES
| PROJECT CLASSIFICATIONS | YES
| PROJECT LABOR COSTS | YES
| PROJECT NONLABOR COSTS | YES
| PROJECT MISCELLANEOUS COSTS | YES
| RESOURCE BREAKDOWN STRUCTURE | YES
PURCHASE ORDERS | HEADERS | YES | YES
| DISTRIBUTIONS | YES | IN PROGRESS | Sprint 12
| LINES | YES | YES
| LINE_LOCATIONS | YES | YES