## Workcycle20
EPIC | Feature | PBI | Tasks | Assigned to | Days | Reviewer
Maximise Enhancements | HCM Enhancements | Adding Batch_column for HCM Tables | Adding new column for load batch and running ETL for HCM- Part3 | Soundarya | 3 days
|  | DM3-010 documentation of HCM objects | Developing DM3-010 documents for HCM objects | Soundarya
Maximise Enhancements | HCM Enhancements | DM3-010 documentation of HCM objects | Developing DM3-010 documents for HCM objects | Soundarya
Maximise Enhancements | OIC Improvements | Integration changes | Creating of batching for Extract file generation | Latheef | 3 days | Ayush
|  |  | Creating of batching for transform file generation | Latheef | 3 days | Shireesha
Maximise Enhancements | HCM Enhancements | Working on Integration on placing the Load file from DB server to FTP | Working on Integration on placing the Load file from DB server to FTP | Ayush/Shireesha | 5 days | Latheef
|  | To work on Procedure where batching is not enabled | To work on Procedure where batching is not enabled | Ayush | 3 days | Sinchana
Maximise Dashboard | Maximise Dashboard Technical document | Dashboard tech document complete review | Dashboard tech document complete review |  |  | Pallavi/ Praveen